## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Organizing Trello | 1 | 16/05/2023 | Organizing a Trello board and filling it out with the user stories. https://trello.com/b/pPSN3ZC4/dtt-maze-generation
Research maze generation algorithms | 1 | 16/05/2023 | Since I already applied once for an internship with DTT, and that time I had to make a very similar assignment (Including maze generation using Aldous-Broder, Binary Tree, and Prim’s Algorrithm, Random Depth First Search, this time I want to focus on the visualization and gameplay more than the maze generation itself. Thus, I looked at the results of a view perfect maze algorithms and picked the most visually interesting that I haven’t programmed before, Recursive Division. Steps on how that algorithm works are listed at https://weblog.jamisbuck.org/2011/1/12/maze-generation-recursive-division-algorithm
Project Setup and initial maze generation code | 2 | 16/05/2023 | I setup a github repository for the project, and started to get to work. I used the algorithm to fill a cell based grid with walls and passages.
Debugging the ‘perfectness’ of the algorithm | 2 | 16/05/2023 | My algorithm seemed to be generating mazes, but did not seem to generate perfect mazes, as some of the paths were not connected to one another. To fix this, I ended up converting the grid to a grid of vertices between which walls can exist, instead of handling the grid as a grid of cells.
Creating a visual representation with quad mesh generation | 1 | 17/05/2023 | I felt like it would be more fun to have an actual 3d maze than just a 2d representation so I could later add a player controller to try and solve the maze in first person. To test how such a maze would look in 3d, I wrote some code that generates quad meshes for all the walls.
Creating a visual representation with prefab scaling | 1 | 18/05/2023 | The quads showed a nice representation of the maze, but there was something missing: thickness to the walls. So instead, I opted to make two prefabs for the outer and inner walls that are then appropriately scaled and placed into position.
Creating responsive UI to change the generation parameters | 1 | 18/05/2023 | I created some UI elements that are all scaled to the respective screen size, that allow you to input an X and Y value for the grid size, and then also added a button that starts the maze generation. I also did some input validation and wrote a script that enables/disables the generate button based on whether the generation parameters are satisfied
Maze configuration limits and camera scaling | 1 | 18/05/2023 | Made sure mazes of only certain sizes can be input into the UI. Also added a component that scales the camera size appropriately.
Design, color schemes and adding optional features to trello | 1 | 18/05/2023 | Worked out the idea for the optional features that I want to implement. Then I started designing some color schemes for the game to adhere to, and added the optional features I want to implement to the trello board.
Minimizing UI | 1 | 18/05/2023 | Adding a minimize button to the UI including an open/close animation, and making it look pretty. | x
Total amount of hours | 11