## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Organizing Trello | 1 | 16/05/2023 | Organizing a Trello board and filling it out with the user stories. https://trello.com/b/pPSN3ZC4/dtt-maze-generation
Research maze generation algorithms | 1 | 16/05/2023 | Since I already applied once for an internship with DTT, and that time I had to make a very similar assignment (Including maze generation using Aldous-Broder, Binary Tree, and Prim’s Algorrithm, Random Depth First Search, my project from that time can be found at https://github.com/kemmel-dev/MazeGen/ ), this time I want to focus on the visualization and gameplay more than the maze generation itself. Thus, I looked at the results of a view perfect maze algorithms and picked the most visually interesting that I haven’t programmed before, Recursive Division. Steps on how that algorithm works are listed at https://weblog.jamisbuck.org/2011/1/12/maze-generation-recursive-division-algorithm
Project Setup and initial maze generation code | 2 | 16/05/2023 | I setup a github repository for the project, and started to get to work. I used the algorithm to fill a cell based grid with walls and passages.
Debugging the ‘perfectness’ of the algorithm | 2 | 16/05/2023 | My algorithm seemed to be generating mazes, but did not seem to generate perfect mazes, as some of the paths were not connected to one another. To fix this, I ended up converting the grid to a grid of vertices between which walls can exist, instead of handling the grid as a grid of cells.
Creating a visual representation with quad mesh generation | 1 | 17/05/2023 | I felt like it would be more fun to have an actual 3d maze than just a 2d representation so I could later add a player controller to try and solve the maze in first person. To test how such a maze would look in 3d, I wrote some code that generates quad meshes for all the walls.
Creating a visual representation with prefab scaling | 1 | 18/05/2023 | The quads showed a nice representation of the maze, but there was something missing: thickness to the walls. So instead, I opted to make two prefabs for the outer and inner walls that are then appropriately scaled and placed into position.
Creating responsive UI to change the generation parameters | 1 | 18/05/2023 | I created some UI elements that are all scaled to the respective screen size, that allow you to input an X and Y value for the grid size, and then also added a button that starts the maze generation. I also did some input validation and wrote a script that enables/disables the generate button based on whether the generation parameters are satisfied
Maze configuration limits and camera scaling | 1 | 18/05/2023 | Made sure mazes of only certain sizes can be input into the UI. Also added a component that scales the camera size appropriately.
Design, color schemes and adding optional features to trello | 1 | 18/05/2023 | Worked out the idea for the optional features that I want to implement. Then I started designing some color schemes for the game to adhere to, and added the optional features I want to implement to the trello board.
Minimizing UI | 1 | 18/05/2023 | Adding a minimize button to the UI including an open/close animation, and making it look pretty. | x
Refine camera scaling, and add pan and zoom camera controls | 1 | 19/05/2023 | The camera scaling seemed to run into some issues here and there, so I updated it to take the horizontal aspect ratio in mind. I also added some camera controls that allow you to pan and zoom around the maze. | x
Step by step maze building. | 1 | 19/05/2023 | Added coroutines to visualize the steps that the algorithm takes, and made sure that these were stopped when restarted. They also take into account a config value of StepTime which indicate how long a build step takes. | x
Improving 2D performance by adding a 2d renderer | 1 | 19/05/2023 | Since the meshes for 250x250 mazes contain quite a lot of vertices, the performance in the maze overview was pretty bad. We don’t need to generate the 3d meshes before we actually jump into the 3d view, So I extracted an interface for the mazebuilder and added one that drew the maze using linerenderer components instead. Still not the best performance solution (Best would be to convert the results into static images), but the performance will be okay for a mostly static scene. The algorithm still causes a little bit of a lagspike when initially generating the maze, but the performance of the algorithm can only be improved marginally. I chose not to work on a more performance-friendly algorithm as I already showed how I would do that in my previous internship application ( https://github.com/kemmel-dev/MazeGen/ )
Total amount of hours | 12